## Critical Path Method
Critical Path Method
Note: The CPM should be done in an external app/hand drawn OR in the table.
Task ID | Task | Dependency | Duration (Months) | Discussion/Reference | Relationship | Tasks
1.1 | Security Architecture Design | — | 2 | Defines camera placement and biometric zones; required before procurement. | Finish-to-Start (FS) | Task 2.1 (Hardware Procurement) $\rightarrow$ Task 3.2 (Physical Installation)
1.2 | Network & AI Integration Plan | 1.1 | 2 | Technical planning for AI server data flow and storage requirements. | Start-to-Finish (SF) | Task 5.1 (System Handover) $\rightarrow$ Task 5.2 (Continuous 24/7 Operations)
2.1 | Hardware Procurement | 1.2 | 4 | Lead time for 160 cameras, 300 sensors, and 45 biometric scanners. | Start-to-Start (SS) | Task 3.1 (Site Prep & Wiring) $\rightarrow$ Task 3.2 (Physical Installation)
3.1 | Site Prep & Wiring | 1.2 | 3 | Physical preparation of the facility; can start parallel to procurement. | Finish-to-Finish (FF) | Task 4.1 (AI Server & Storage Setup) $\rightarrow$ Task 4.2 (System Calibration & Testing)
3.2 | Physical Installation | 2.1, 3.1 | 6 | Mounting hardware and connecting to the network backbone.
4.1 | AI Server & Storage Setup | 2.1 | 3 | Configuring the 2.5 kW AI processing units and data storage.
4.2 | System Calibration & Testing | 3.2, 4.1 | 2 | Tuning motion sensors and biometric scanner accuracy.
5.1 | Security Audit & Handover | 4.2 | 1 | Final safety certification and transition to operational staff.
5.2 | Continuous 24/7 Operations | 5.1 | 37 | Ongoing monitoring and maintenance for the remainder of the 5-year term.

## Cost Benefit Analysis
Category | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Capital Costs (CapEx) | -$368,500 | 0 | 0 | 0 | 0
Operating Costs (OpEx) | -$24,646 | -$24,646 | -$24,646 | -$24,646 | -$24,646
Benefits (Monetized) | $0 | +$45,324 | +$45,324 | +$45,324 | +$45,324
Net Cash Flow (Total) | -393146 | 20678 | 20678 | 20678 | 20678