## Risk Matrix
Design 1: | Protect the facility from data breaches and other cybersecurity attacks | Design 2: | Balanced cost, durable Electrical Security System w/ 95% area surveillance
Exercise 1 & 2
| Risks | Likeliness | Frequency per Year | MTTH (annual) | MTTH (months to occur) | Impact Low: <$10,000 Medium: $10,000-$100,000 High: >$100,000 | Discussion
1 | Operating Cost Variability Due to Cloud and Energy Use | 100% chance each year | 1 time(s)/Year | 1 yr(s) | 12 months | Medium (~$45,000) | Cloud and energy costs fluctuate due to usage spikes, vendor pricing changes, and energy market shifts. 84% of organizations struggle to manage cloud spend (Flexera, 2024: https://www.flexera.com/stateofthecloud). 1 in 3 businesses exceed cloud budgets by 20-40% (Pepperdata, 2021: https://www.pepperdata.com/pepperdata-new-survey-cloud-budgets). Data centre energy use is projected to double from 415 TWh (2024) to 945 TWh by 2030, driven by AI (IEA, 2025: https://www.iea.org/reports/energy-and-ai/energy-demand-from-ai). Mitigation: reserved cloud pricing, real-time cost monitoring, and quarterly FinOps reviews. Hence, the probablity of occurrence is high and impact is medium. The impact is medium because a 20-40% increase in cloud budget per year in 33% of companies is not a staggering statistics. If the increase were more than 50% per year, we could have classified it as High Impact. Also, the impact dollar value per year is $45000. The average enterprise wastes 32% of cloud spend, with cloud projects coming in 13% over budget on average. Mid-sized companies spend roughly $2–5 million annually on cloud services, placing 30% waste at $60K–$150K. For a smaller budget of ~$150K/year, 30% waste = ~$45,000. (Flexera via Tech Monitor: https://techmonitor.ai/technology/cloud/cloud-spending-wasted-oracle-computing-aws-azure; DataStackHub Cloud Spend Statistics 2025: https://www.datastackhub.com/insights/cloud-spend-statistics/)
2 | Uncertainty in Time for Certification of Cybersecurity for Whole System | 2% chance per year | 0.02 times/Year | 50yr(s) | 600 months | Medium (~$40,000) | Cybersecurity certification and audit timelines are often longer than teams expect because there is a readines phase plus audit or testing and report issuance. Industry timeline for SOC 2 Type 1 commonly take about 3-6 months end-to-end and Type 2 can take 6-12 months or longer due to the required observation period and remediation if gaps are found. This creates schedule risk for our project because if certification takes longer than planned, commissioning and handover can be delayed and benefits may start later.[Link] https://www.dsalta.com/resources/soc-2/soc-2-type-1-vs-type-2-timeline-cost-guide ; https://trustnetinc.com/resources/hub/soc-2/audit-process-timeline-costs/
3 | Uncertainty in Updating of Cybersecurity | 100% chance each year | 1 time(s)/Year | 1 yr(s) | 12 months | High (~$200,000) | This risk impacts the software security subsystem. Generally, major gaps in cybersecurity are determined annually and must be fixed prompty to ensure the protection of the system (https://www.uzado.com/blog/how-often-should-you-update-your-cyber-security-policy/). The impact for this is quite high; if major gaps are found, there must be extensive revamping of the software system depending on new vulnerabilities discovered and the general state of cybersecurity practices throughout the world. For a facility such as ours, it is likely that revamping the cybersecurity system will cost approximately $200,000 (https://frameworksecurity.com/post/how-much-does-cybersecurity-really-cost). This risk primarily affects schedule as if the cybersecurity cannot be prompty updated the software subsystem may need to be temporarily shut down to avoid breaches.
4 | Hardware Failure/Need for Immediate Maintenance | 13% chance per year | 0.13 times/Year | 7.6923 yr(s) | 92.3 months | Medium (~52,500) | This risk impacts primarily the electrical subsystem, and it affects mainly the schedule, as the time it takes to reorder and install hardware parts could be up to a week. The price of labour workers (security services) to work in place while the system is down is also another factor. For cloud-based data centres, the probability of hardware failure accumulates over time; large-scale studies of production systems report non-trivial failure rates, with disk drive annual failure rates ranging from roughly 1.7% to over 8% in large cloud deployments. https://static.googleusercontent.com/media/research.google.com/en//archive/disk_failures.pdf. Hardware maintenance covers storage, server, and network hardware — all critical components of IT infrastructure; if a device malfunctions, support must be on-hand to repair equipment promptly, with OEM services available though third-party maintenance providers are typically cheaper without a drop in quality. Component-level server replacement ($15K–$40K) plus emergency labour ($10K–$15K) and 1–3 days of partial downtime yields ~$52,500 per incident. (Park Place Technologies Data Center Maintenance Guide: https://www.parkplacetechnologies.com/blog/data-center-maintenance-guide-best-practices-prevent-downtime/) https://info.pivitglobal.com/blog/causes-of-hardware-failure
Impact
|  | Low (<$10,000) | Medium ($10,000-$100,000) | High (>$100,000)
Probability | Low (>15 years) |  | Uncertainty in Time for Certification of Cybersecurity for Whole System (50 years, ~$40,000)
| Medium (5-15 years) |  | Hardware Failure (7.7 years, ~$40,000)
| High (<5 years) |  | Operating Cost Variability Due to Cloud and Energy Use (1 year, ~$45,000) | Uncertainty in Updating of Cybersecurity (1 year, ~$200,000)
Exercise 3:
Risk Driver | Uncertainty Range | Appropriate Distribution | Discussion |  |  | Definitions
Uncertainty in Updating of Cybersecurity | +-50% | Normal Distribution | This risk follows a normal distribution as there is an average that updating cybersecurity generally costs. However, there are many variables that could increase or decrease the cost of updating the cybersecurity (e.g., new vulnerabilities discovered, new attacks become popular/known to the public, etc.). This leads to extreme cases both where it could cost much more if a large vulnerability is discovered, or could cost very little if nomajor updates are required for the year. Due to this large variance, the cost/impact could easily be greatly increased or decreased depending on the circumstances of the particular year (hence the uncertainty range of +-50%). |  |  | Uniform Distribution: Use when you only know bounds and extremes are just as likely as central value
Operating Cost Variability Due to Cloud and Energy Use | +-50% | Lognormal Distribution (found from page 26 of lecture 14) | Cloud pricing is positively skewed; costs are bounded at zero but can spike sharply during high-demand periods or after vendor price increases. A Log-Normal distribution captures this asymmetry well. LSTM-based models reduce cloud cost prediction error (MAPE) from 26.7% to 9.8% vs. traditional ARIMA models (WJAETS, 2025: https://journalwjaets.com/sites/default/files/fulltext_pdf/WJAETS-2025-0218.pdf). Flexera (2024) reports 84% of organizations struggle with cloud spend management: https://www.flexera.com/stateofthecloud |  |  | Normal Distribution: Use when values cluster around a mean (𝜇) symmetrically.
Hardware Failure | +-7.5% | Discrete Distribution | In the case of hardware failures, there is a binary outcome for any piece of hardware; therefore, it follows a discrete distribution. As determined earlier, there is a 13% chance for a failure to occur for any piece of hardware. Consequently, each individual unit acts as a Bernoulli trial, where the hardware exists in one of two mutually exclusive states: operational (0) or failed (1). Uncertainty stems from the number of pieces of hardware used across the entire system. |  |  | Discrete Scenarios: Use when outcomes are “case-based”
Uncertainty in Time for Certification of Cybersecurity for Whole System | +-1% | Uniform Distribution | The certification timeline uncertainty is narrow and bounded at ±1%, with no single value within that range more probable than another. A Uniform Distribution is applied following the GUM (JCGM 100:2008) standard, which states that when only upper and lower bounds are known, Uniform is the appropriate assumption (https://www.bipm.org/documents/20126/2071204/JCGM_100_2008_E.pdf). This reflects a well-controlled certification process with stable regulatory requirements. Mitigation: maintain continuous compliance documentation and conduct pre-certification readiness assessments.
Exercise 4:
Risk | Mitigation Strategy | Cost of Implementation | Discussion
Uncertainty in Updating of Cybersecurity | Throughout the year, a cybersecurity expert should keep up to date on the popular attacks and vulnerabilities. Additionally, regular maintenance should take place to the cybersecurity system to lessen the chance of major revamps needing to take place. Furthermore, documentation and clean networking / code can help to lessen the difficulty in revamping the code if necessary. | To implement this, we would need to hire a cybersecurity expert to work year round implementing the mitigation strategy. This would cost approximately $104,224 (https://ca.indeed.com/career/cybersecurity-specialist/salaries). | By keeping up to date on popular attacks and vulnerabilities, the delay in determining how to revamp the cybersecurity system will be minimized (because we will already be knowledgeable on common issues). Regular maintenance will lessen the chance of major cybersecurity revamps occuring. Documentation and clean networking / code will lessen the impact of having to revamp the cybersecurity system by making the system easier to update. By implementing these strategies, we expect to reduce this risk's probability by 25% (https://www.dartai.com/blog/how-does-documentation-manage-risk). Additionally, this strategy can reduce the impact of the risk by approximately 50% (https://awaywithwords.co/2024/09/18/statistics-and-facts-supporting-the-importance-of-software-documentation-away-with-words/).
Operating Cost Variability Due to Cloud and Energy Use | Reserved cloud pricing, real-time cost monitoring, and quarterly FinOps reviews | ~$6,000–$60,000/year — $0 using native cloud tools (AWS Cost Explorer, Azure Cost Management) or $500–$5,000/month for third-party platforms (e.g., Flexera, CloudChipr), plus internal staff time of 1–2 FTE days per quarter for FinOps reviews. Reserved cloud pricing requires no upfront cost and can save up to 60% on compute vs. on-demand rates. | Reserved Instances and Savings Plans deliver up to 60% savings on compute costs, with proactive budget controls reducing unexpected cost incidents by 35% (FinOps Benchmark 2024: https://www.quinnox.com/blogs/finops-best-practices/). Native tools like AWS Cost Explorer and Azure Cost Management provide real-time monitoring at no cost, helping identify wastage — critical given 82% of organizations waste at least 10% of cloud spend (Flexera 2024: https://www.flexera.com/stateofthecloud). Quarterly FinOps reviews align engineering and finance teams on spend accountability (FinOps Foundation: https://www.finops.org).
Hardware Failure | To combat the potential risk of hardware failures, the system can maintain an N+1 redundancy for all units. This entails keeping a spare duplicate hardware component on-site at all times. Also, to prevent continual issues within the hardware, scheduled maintenance check-ups and replacements should be employed to ensure all equipment is upto standard. | This strategy increases both inital captial expediture and operating expediture. Ordering two times as many components will effectively double the cost, and scheduling routine hardware check-ups will increase labour costs. | By implementing these changes, the probability of a total hardware failure decreases from p to p^2. The probability of a total system outage is no longer 13%. It is now the probability of two specific units failing within the same repair window. For a 13% risk, the likelihood of a total blackout drops from 13% to roughly 1.69%. Routine check-ups increase reliability of the system. Simple tasks to manage thermal and physical stress of the system will significantly redeuced the probability of failure.
Uncertainty in Time for Certification of Cybersecurity for Whole System | Start certification planning early. Do a readiness check before the audit, freeze the system scope during the audit window, and keep a buffer for fixes or refesting so certification does not block go-live. | TrustNet reports that SOC 2 Type 1 audits commonly cost about $10,000–$25,000, while Type 2 audits are often $20,000–$60,000 (and can be higher for complex systems). Main cost is staff time for documentation and audit prep, plus possible external auditor/support fees. Reference: SOC 2 timeline and effort typically requires readiness work and audit time (DSALTA): https://www.dsalta.com/resources/soc-2/soc-2-type-1-vs-type-2-timeline-cost-guide | Certification can take longer than expected because teams must collect evidence, close gaps, and sometimes repeat testing. If it slips, it delays commissioning and pushes benefits later. Starting early and adding schedule buffer reduces the chance that certification becomes the critical delay. Reference (https://trustnetinc.com/resources/hub/soc-2/audit-process-timeline-costs/).
Note: To incorporate the mitigation strategies into our economic model, we can use stochastic modelling for the risks, then add the reductions to the impact and/or probability based on our estimated values from above for the mitigation strategies. We would then also add the costs of implementing the mitigation strategies.
Exercise 5:
Discussion:
Uncertainty in Updating of Cybersecurity is one of the risks that dominates our project. This is because this risk has a very high impact(~$200,000) and high likelihood (once per year). This makes sense as cybersecurity is a very common issue for companies today and requires constant attention to stay relevant and safe.
Uncertainty makes us less confident in our earlier economic conclusions. Before, our economic conclusions assumed that everything went as planned. However, after these excersizes it is clear that many things could go wrong, delaying our project, increasing the cost, etc. More work should be done to implement uncertainty into our economic calculations.
One limitation remaining in our current model is that we have not actually incorporated these risks and mitigation strategies into our economic model yet. Another limitation is that we have only identified a small number of the total potential risks for the project. In a real world setting, we would have to spend much more time identifying and mitigating more risks.